## Status Summary
BRv4 defect status - updated 2026-10-12 (QA live retest + dev response + DEF-017 dev triage + DEF-017 QA retest + DEF-017 regression retest)
Final Classification | Count | Bugs
Valid defect | 3 | DEF-004, DEF-009, DEF-011
Valid defect (partial) | 0 | -
Valid defect (duplicate) | 1 | DEF-012
Needs investigation | 0 | -
Spec conflict | 1 | DEF-002
Working to spec (enhancement) | 1 | DEF-006
Not a defect | 8 | DEF-001, DEF-003, DEF-005, DEF-007, DEF-008, DEF-010, DEF-014, DEF-016
Not a defect (test data / test design) | 3 | DEF-013, DEF-015, DEF-017
Total | 17
Retest needed? | Count | Bugs
Yes - re-targeted TC | 5 | DEF-016
After decision | 1 | DEF-002
After merge | 5 | DEF-004, DEF-006, DEF-009, DEF-011
Yes - after harness fix | 1 | DEF-007
After fix | 0 | -
With DEF-004 | 0 | DEF-012
Yes - reseed | 1 | DEF-013
Optional regression | 1 | DEF-014
Owner / next move | Bugs
Dev: merge the fix branch | DEF-004, DEF-012, DEF-006 (BR-419), DEF-009, DEF-011 - all valid defects now fixed; 958/958 unit + 206/206 integration tests green
Dev: apply fix patch (DEF-009, DEF-011) - done in patch | brv4-fixes-DEF-004-006-009-011-full.patch (on develop) or ...-DEF-009-011-incremental.patch (on the existing branch)
BA / PO decision | DEF-002 (BR-134 wording), DEF-006 (WARN for CRD > 8), DEF-007 (BR-459 value), DEF-014 (reword BR-088), DEF-017 (BR-436: should a BD be able to drop its ALT_ADDRESS via the feed?)
QA: re-targeted retests (can start now) | DEF-001, 003, 005, 008, 010, 013; DEF-017 done 2026-10-05 (TC-BR-436 re-targeted to expect C0708, retested PASS 6/6)
QA: harness fixes first | DATE as text (DEF-007/004), assert on LNAERROR (DEF-005/008), node ids <= 11 digits (DEF-013)
Note | COBOL checked 2026-09-30 against ADSI_Allstate_POC/SRC (UTP27201, UTP27801, UTP27901). DEF-009 was re-added: it was dropped from QA's list, but the COBOL confirms it.
Fix status (2026-09-30) | Count | Bugs
Fixed (QA-verified: 004, 006, 012; 011 partly; 009 awaiting retest) | 5 | DEF-004, DEF-006, DEF-009, DEF-011, DEF-012
No fix needed | 11 | DEF-001, DEF-003, DEF-005, DEF-007, DEF-008, DEF-010, DEF-013, DEF-014, DEF-015, DEF-016, DEF-017
Pending BA decision | 1 | DEF-002
Branch | ai/JhomariAtienza2/brv4-dob-default-crd-compare
Verification | 958/958 unit + 206/206 integration tests green; the new tests fail on the old code. Local mvn test (Testcontainers) and commit/PR still to do.
Note | DEF-004 and DEF-012 are one fix, so 4 distinct defects are fixed across 5 tickets.
--- QA Live Retest Update (2026-09-30, fresh env, dev fix confirmed deployed) ---
DEF-004, DEF-006, DEF-007, DEF-008, DEF-005, DEF-010, DEF-011 (TC-BR-051/318 only), DEF-012, DEF-014 | PASS - confirmed deployed and working, or confirmed not-a-defect, on live retest. See each bug's "QA Live Retest" column for specifics.
DEF-001 | B0606 sub-scenario confirmed correct; B0608 sub-scenario revealed a new gap - see DEF-015.
DEF-002 | Retested with the P2721 scenario; reported factually, still awaiting the BA's decision.
DEF-013 | RETRACTED by QA - confirmed test data (oversized synthetic subject_id). Reseeded correctly, no crash, all sibling TCs pass.
DEF-003, DEF-009, DEF-011 (TC-BR-319 only) | Could not be independently confirmed - see DEF-016 below.
DEF-015 (NEW) | B0608 (blank correspondence address on the first BD firm) does not reject the bundle, while the sibling B0606 validation correctly does.
DEF-016 (NEW, HIGH, URGENT) | contract_history / node_relationship_history / address-on-create writes appear broken for genuine changes, not just no-ops - confirmed in isolation on a clean DB via an unmodified, previously-passing test (TC-BR-050). Likely a side effect of DEF-011's own fix.
2026-10-01 note | DEF-015: not a defect - QA's own feed is rejected with B0608; the evidence came from a run-log check (codes go to LNAERROR) and a stale organisation row. DEF-016: not a defect - person-field triggers never write contract/relationship history in legacy; re-target the TCs.
2026-10-01 QA recheck | Both DEF-015 and DEF-016 confirmed NOT a defect after dev's response - QA's own test constructions were wrong, not the app. Corrected TCs (BR-016, BR-050, BR-319, BR-140) all rerun live and pass.
2026-10-02 QA - DEF-017 (NEW) | TC-BR-436 (the only failure in the 2026-10-01 BRv4 run, 155/156 passed): a standalone BD update that blanks the whole correspondence (mailing) address completes with no LNAERROR/ADBSKIP/ADBERROR and CNTLRPT counts 1 BD contract updated, but the MAILING row, contract updt_ts and activity log are untouched, so the master keeps ALT_ADDRESS (basic4 3 -> 3). Feed byte-verified; the same C-only path works for BUSINESS (TC-BR-325/053/088 pass). HR2 is correct; the fault is in HR1. Awaiting dev triage against UTP27201.
2026-10-05 dev triage - DEF-017 | Not a defect (test design). A standalone BD record with a wholly blank correspondence block is rejected with C0708 before any write (FeedRecordValidator, legacy 8005; reproduced against the built code), and the BD MAILING row is never deleted by design, so TC-BR-436's expected 3 -> 2 basic4 change is not reachable via the feed. QA's observed result (no LNAERROR, CNTLRPT 1 BD updated, nothing changed) cannot come from the described feed: QA to recheck which day-2 file was ingested, then re-target TC-BR-436. BA to confirm BR-436 intent.
2026-10-05 QA retest - DEF-017 | Closed - not a defect (test design), confirmed via re-targeted TC-BR-436, live PASS 6/6: blank correspondence block on a standalone BD rejected with C0708, CNTLRPT BD updated = 0, no ADB/ADSI change. Open: BA/PO to confirm BR-436 intent (no feed path lets a BD drop ALT_ADDRESS). Side note for dev: the 2026-10-01 run outcome (no C0708, BD updated = 1, no address row inserted) remains unexplained - likely a different build at the time.
2026-10-12 QA regression - DEF-017 | QA regression retest 2026-10-12 (full BRv4 run, playwright.brv4.config.ts, 165/165 passed): TC-BR-436 PASS 6/6 - day-2 standalone C with a wholly blank correspondence block rejected with C0708 in LNAERROR, CNTLRPT BD contracts updated = 0, no ADB/ADSI change (MAILING row and basic4 ALT_ADDRESS retained). Verdict 2026-10-12 09:49:42Z. Closure holds.

## bug-reports-brv4.csv
Bug ID | Title | Related TC | Rule ID | Classification | Severity | Priority | Environment | Preconditions | Test Data / Feed | Steps to Reproduce | Expected Result | Actual Result | DB Evidence | Evidence / Artifacts | Root Cause | Impact | Reproducibility | Workaround | Recommended Investigation | Dev Verdict | Recommended Disposition | Code Reference (under src/main/java/com/prudential/adb/allstate/hr/) | Code Analysis | Next Step | Recheck 2026-09-30 | Final Classification | Status | Retest Needed? | Owner | Action to Close | Fix Status (2026-09-30) | What Was Fixed | Files Changed | Tests Proving the Fix | Branch | QA Live Retest (2026-09-30, fresh env, fix confirmed deployed) | Dev Response (2026-10-01) | QA Recheck (2026-10-01, after dev response)
DEF-RDMS-BRV4-001 | Mandatory BD field not enforced on bundle rejection | TC-BR-016 | BR-016 | Application Defect | Medium | Not Determined | BRv4 dev console, pru_adb_dev | A feed bundle whose first firm (the broker-dealer) has WS-RES-STATE blank. | ALLSTATE.LNA.BR-016-CANDIDATE.D20260908.txt (verified byte-correct: BD's WS-RES-STATE = two spaces) | Upload a bundle where bundle 1's BD firm has a blank WS-RES-STATE. | The entire bundle is rejected (no organization row created). | The system accepted it and created the organization row anyway (count=1). | pru_adb.organization row exists for the BD's org code. | artifacts/reports/bug-evidence/DEF-RDMS-BRV4-001-BR-016/ (feed file + official ingestion-artifacts + evidence.json) | Probable Root Cause - the mandatory-field check this rule describes does not appear to be enforced in the live application for this field/entity-type combination. | A required business validation may not be applied, allowing incomplete BD records into the system. | Confirmed, single run. | None identified. | Confirm with the dev team whether WS-RES-STATE validation for BD-type firms was intentionally relaxed or is a genuine gap. | Not a defect – test design | Close / re-target | FeedRecordValidator.java:328 (C0706/B0606) and stateFailure() :931-938 | The legacy rule (utp27301_rules.csv #23, 1510-VAL-FIRST-FIRM, line 2250) says WS-RES-STATE 'If present, must be a valid state code'. A blank value is legal in COBOL and the Java code matches it. B0606 fires only for a non-blank, unknown code; the unit test theBdRecordsResidentStateAndBusinessAddressRulesReportB0606AndB0607 covers that. Note: the comment on stateFailure says blank is 'left to the services', but no service checks it. That comment is misleading and should be fixed. | Retest BR-016 with a field that really is BD-only mandatory, e.g. a blank correspondence address on the first firm (C0708/B0608 is mandatory only for BD), or an invalid (non-blank) resident state such as 'ZZ' → expect B0606 and bundle rejection. | Unchanged since the last review; verdict stands. | Not a defect | Closed - QA retest PASS (B0606) | Done | QA | Retest TC-BR-016: blank correspondence address on the first BD firm -> B0608, bundle rejected. Add WS-RES-STATE='ZZ' -> B0606. | No fix needed - not a defect | - | - | - | - | Retested per dev's clarified scenario. B0606 (WS-RES-STATE='ZZ') confirmed correctly rejects the bundle. B0608 (blank correspondence address) does NOT reject the bundle - filed as new defect DEF-RDMS-BRV4-015. | Accepted. B0606 behaves as expected. The B0608 claim is tracked in DEF-015, but it could not be reproduced (see DEF-015). Close DEF-001.
DEF-RDMS-BRV4-002 | Type-H (history-only) profile creates a live contract record | TC-BR-134 | BR-134 | Application Defect | Medium | Not Determined | BRv4 dev console, pru_adb_dev | A producer profile record with WS-PROF-TYPE = 'H'. | ALLSTATE.LNA.BR-134-CANDIDATE.D20260908.txt | Upload a producer with a type-H profile. | No live pru_adb.contract row created; history-only, logged to history table only. | A live contract row was created (count=1). | pru_adb.contract row exists for the type-H producer's allstate_id. | artifacts/reports/bug-evidence/DEF-RDMS-BRV4-002-BR-134/ (feed file + official ingestion-artifacts + evidence.json) | Probable Root Cause - the history-only exclusion for type H does not appear to be applied. | History-only profiles may be incorrectly treated as active/live records downstream. | Confirmed, single run. | None identified. | Confirm intended handling of WS-PROF-TYPE = 'H' with the dev team. | Spec conflict – code follows COBOL | Needs BA decision | ProducerAppointmentServiceImpl.java:590-620 (appointProducer, HISTORY_ONLY branch) | A HISTORY_ONLY ('H') profile is rejected only when the producer's contract already exists but has no relationship. A producer ADB has never seen goes through insertProducer like a 'C' profile. The code comment cites UTP27201 5000-PERS-PROCESS-PARA lines 3937-3964: the CHLD-NODE-FOUND='N' branch calls 3170-INSERT-PROFILE-INFO without testing profile type. The BRD ('can never bring an appointment into being', reject with P2721) contradicts this reading of the legacy code. | BA/SME to confirm which is authoritative: the COBOL behaviour (insert a brand-new H producer) or the BRD wording (reject). If the BRD wins, change the 'existing.isPresent() && !relationshipExists' guard to reject every HISTORY_ONLY with no relationship. | Unchanged since the last review; verdict stands. | Spec conflict | Blocked - BA decision | After decision | BA | BA decides COBOL parity (current code) vs. the BRD wording. Retest the P2721 case (existing producer under firm X, 'H' profile under firm Y) now. | Pending BA decision - no code change yet | - | - | - | - | Retested with the P2721 scenario (real appointment under firm X, then a type-H profile fed under a different firm Y for the same person). Both cycles completed; reported factually for the BA's pending decision, not asserted right or wrong. | Noted; still waiting on the BA decision.
DEF-RDMS-BRV4-003 | Blank home address on a new record produces no address row | TC-BR-140 | BR-140 | Application Defect | Low | Not Determined | BRv4 dev console, pru_adb_dev | A brand-new producer with WS-HOME-ADD-L1/CITY/ST-CD/ZIP-CD all blank. | ALLSTATE.LNA.BR-140-CANDIDATE.D20260908.txt | Upload a brand-new producer with a completely blank home address. | A pru_adb.address row is still inserted (empty), not skipped. | No address row was created at all. | pru_adb.address has zero rows for this producer's SSN/contract number with address_type='HOME'. | artifacts/reports/bug-evidence/DEF-RDMS-BRV4-003-BR-140/ (feed file + official ingestion-artifacts + evidence.json) | Probable Root Cause - the insert-even-if-blank behavior this rule documents does not appear to be applied. | Downstream consumers expecting an (empty) address row may instead see no row at all for brand-new, address-less records. | Confirmed, single run. | None identified. | Confirm with the dev team whether this insert-even-if-blank behavior is still intended. | Not a defect – wrong path tested | Close / re-target | ProducerAppointmentServiceImpl.java:1084-1140 (applyProducerAddresses) | Deliberate legacy parity. On a brand-new contract, UTP27201:3092-3093 guards the home-address block on a non-blank line 1, so no row is written. The blank insert that BR-140 describes happens only on the UPDATE path (3150-ADDRTYPE-A, :1568), and the code does insert it there. This was validated against the mainframe: Day 1 has 41 contracts with no site type, and Day 2 has 12 that gain one. | Retest with an EXISTING producer that has no HOME address row, sending a fully blank home address → expect an empty HOME row to be inserted. | Unchanged since the last review; verdict stands. | Not a defect | Closed - behaviour confirmed (dev repro) | Re-run with the correct query | QA | 3-feed update-path scenario for TC-BR-140. Ask the BA to reword BR-140. | No fix needed - not a defect | - | - | - | - | Day1 (blank HOME address on a brand-new record) could not be re-confirmed this round - see DEF-RDMS-BRV4-016 (broader regression: no address row of any kind is currently created for a new record's blank address block). | DEF-016 does not block this one. A brand-new producer with a blank home block correctly gets NO HOME row (UTP27201 :3092 guard). Its BUSINESS row is keyed by contract number, not SSN, so a query by SSN returns []. Reproduced 2026-10-01: day 1 gives [BUSINESS:<contract no>] and no HOME; the day-2 update gives an empty HOME row. Mark PASS.
DEF-RDMS-BRV4-004 | Blank DOB leaves birth_date NULL instead of a placeholder | TC-BR-321 | BR-321 | Application Defect | Low | Not Determined | BRv4 dev console, pru_adb_dev | A brand-new producer with WS-DOB blank. | ALLSTATE.LNA.BR-321-CANDIDATE.D20260908.txt | Upload a brand-new producer with a blank date of birth. | pru_adb.person.birth_date populated with a placeholder value. | birth_date is NULL. | pru_adb.person.birth_date = NULL for this producer's SSN. | artifacts/reports/bug-evidence/DEF-RDMS-BRV4-004-BR-321/ (feed file + official ingestion-artifacts + evidence.json) | Probable Root Cause. | Downstream reports that cannot handle a NULL date (per the rule's own stated rationale) may fail or misbehave for these records. | Confirmed, single run. | None identified. | Confirm intended placeholder value with the dev team. | Valid – confirmed in code | Fix (Low) | ProducerAppointmentServiceImpl.java:2132-2140 (newPerson) and :2074 (applyPersonDetails); FeedRecordMapper.date() returns null for blank | person.setBirthDate(profile.dateOfBirth()) stores null. No placeholder is applied at the ADB (person) level. The placeholder (0001-01-01) is substituted later, only when the master record is built (AdsiMasterRecordBuilder BIRTH_DATE_SENTINEL :246/:652). So the ALADSI10 output matches the mainframe, but pru_adb.person differs from BR-321. | Confirm the legacy placeholder value (the master evidence points to 0001-01-01). Apply it in newPerson (and decide whether update should overwrite an existing DOB with the placeholder when the feed is blank). Keep or remove the builder sentinel; it becomes redundant. | Unchanged. FIXED on branch ai/JhomariAtienza2/brv4-dob-default-crd-compare (not yet merged). Retest after merge: expect 0001-01-01. | Valid defect | Fixed - QA retest PASS (deployed) | Done | Dev -> QA | Merge ai/JhomariAtienza2/brv4-dob-default-crd-compare. Retest: blank DOB on a new producer -> person.birth_date = 0001-01-01 (read as text). | Fixed - on branch, QA-verified PASS | A blank or all-zero WS-DOB is stored as 0001-01-01 for a new producer (UTP27201 3172 :3325). | ProducerAppointmentServiceImpl (birthDateOf, newPerson) | ProducerBirthDateDefaultTest; ProducerAppointmentServiceIT#aNewPersonWithABlankDateOfBirthIsStoredWithThePlaceholderDate | ai/JhomariAtienza2/brv4-dob-default-crd-compare | PASS - confirmed deployed and working: blank DOB on a new producer now stores 0001-01-01.
DEF-RDMS-BRV4-005 | Second producer under the same firm silently dropped | TC-BR-464 | BR-464 | Application Defect | High | Not Determined | BRv4 dev console, pru_adb_dev | One bundle: one firm + two producers (one 'T' with an end date, one 'I' open-ended). | ALLSTATE.LNA.BR-464-CANDIDATE.D20260908.txt | Upload one bundle containing a firm and two producers under it. | Both producers created in pru_adb. | The second producer was never created in pru_adb.person/pru_adb.contract at all (no row, no error), reproduced on 2 independent runs with fresh, collision-free identities. Re-tested with a longer (30s) post-settle wait: the first producer's own sync to adsi_master.contract_record then completed successfully, so that earlier symptom was a sync-latency artifact of an insufficient wait, not a permanent defect - narrowing this bug report to the second-producer-dropped finding specifically, which remains confirmed. | pru_adb.person/pru_adb.contract has exactly 1 row (the first producer) where 2 were expected, on both runs; run log reports the bundle fully committed with 0 records skipped. | artifacts/reports/bug-evidence/DEF-RDMS-BRV4-005-BR-464/ (feed file + official ingestion-artifacts + evidence.json) | Root cause not yet determined; further developer investigation is required. | High - silent data loss for a real, valid bundle; no error, warning, or skip signal is raised. | Confirmed, reproduced on 2 independent runs with different identities. | None identified. | Dev team review of multi-producer bundle handling under one firm - why the second producer's record is never persisted despite the run reporting full success. | Not a defect – record rejected with F0112 | Close / re-target | FeedRecordValidator.java:589-600 (F0111/F0112 date window); AllstateFeedIngestionServiceImpl.java:468 (log line) | The second producer has status 'I' with end date 99999999. The COBOL rule (#72, 4400-VALIDATE-TERM-DATE) needs a real end date for I/T, and 99999999 is only allowed for A. The record was rejected and written to LNAERROR: 'F0112 RELATIONSHIP END DATE INVALID ... RECORD REJECTED'. It was not dropped silently. The '0 record(s) skipped' log line counts ADBSKIP entries only, not LNAERROR rejections, which is what misled the test. BR-464 itself is an HR2 rule (final_date/final_org_code on the master record), and its no-end-date case cannot be fed through HR1. | Test BR-464 with the DB seed approach in the BRD (Sample-BR447-BR464), or with an I/T producer that carries a real end date. Optional improvement: add a 'N record(s) rejected' count to the HR1 completion log line. | Unchanged since the last review; verdict stands. | Not a defect | Closed - QA retest PASS | Done | QA | The record was rejected with F0112 (bad test data). Re-target TC-BR-464 to the HR2 DB-seed approach. Log enhancement: rejected-record count in the HR1 log. | No fix needed - not a defect | - | - | - | - | PASS - re-targeted to the DB-seed + HR2-trigger technique (the original feed combination is invalid test data). Terminated-with-date shows both final_org_code and final_date; DB-seeded inactive-without-date shows final_org_code with NULL final_date.
DEF-RDMS-BRV4-006 | CRD number silently truncated on the master-file write | (none - general) | (none - found incidentally, not tied to a workbook rule) | DB/Data Defect | Medium | Not Determined | BRv4 dev console, pru_adb_dev | A producer with a 9-10 digit CRD number (valid per the feed layout's own 10-character WS-CRD-NUM field width, and per pru_adb.person.crd_number's varchar(10)). | A producer built with WS-CRD-NUM = '9999999999' (10 nines), during TC-BR-131 development | Upload a producer whose CRD number is 9-10 digits long. | Either the value is preserved in full end to end, or the write is rejected/flagged if it cannot fit downstream. | pru_adb.person.crd_number correctly stores all 10 digits (9999999999). adsi_master.contract_record.crd_number (varchar(8)) silently stores only the first 8 digits (99999999) - truncated with no error, warning, or log line. | Direct comparison of pru_adb.person.crd_number vs. adsi_master.contract_record.crd_number for the same subject. | artifacts/reports/bug-evidence/DEF-RDMS-BRV4-006-CRD-truncation/ (feed file + official ingestion-artifacts + evidence.json) | Confirmed Root Cause - a genuine column-width mismatch between pru_adb.person.crd_number varchar(10) and adsi_master.contract_record.crd_number varchar(8), with the copy step performing a silent truncate rather than validating or erroring. | Medium - any CRD number over 8 digits is silently corrupted in the master/reporting file, with no operational signal that it happened. | Confirmed, single run. | None; this is a data-integrity gap in the mirrored write, not something test data can work around. | Confirm with the dev team whether 9-10 digit CRD numbers are expected in production, and if so, widen adsi_master.contract_record.crd_number or add an explicit overflow check. | Valid – but it matches the mainframe layout | Decide: parity vs. guard (Low) | JdbcAdsiMasterRecordRepository.java:343 truncate(r.crdNumber(), 8); V3 schema crd_number VARCHAR(8); ADSIMSTR.cpy ALL-CRD-NUMBER PIC X(8); AdsiMasterBodyEncoder.java:141 | The truncation is real and silent, but it is deliberate. The ALADSI10 copybook defines ALL-CRD-NUMBER as X(8), so the COBOL MOVE from X(10) cuts it the same way. Widening the column alone would not help, because the fixed-width extract is still 8 bytes. Real FINRA CRD numbers are currently at most 8 digits, so the practical risk is low. | Keep parity, but add a WARN log / error-report entry when crdNumber length > 8 (or validate in HR1). Only widen if downstream consumers of ALADSI10 agree to a layout change. Suggest downgrading severity to Low. | Unchanged. The follow-up CRD comparison fix (BR-419) is on the same branch. | Working to spec (enhancement) | Fixed - QA retest PASS (deployed) | Done | PO / Dev -> QA | Truncation to 8 characters is to spec (BR-450). The follow-up CRD comparison fix (BR-419) is on the branch; retest after merge. The PO decides on a WARN for CRDs longer than 8. | Follow-up fixed - on branch, QA-verified PASS (8-char cut is to spec) | The CRD is cut to 8 characters when the master record is built, so HR2 change detection no longer flags CRD_NUMBER on every run for 9-10 digit CRDs (BR-419). The WARN for CRD > 8 awaits a PO decision. | AdsiMasterRecordBuilder (toMasterCrdNumber) | AdsiMasterRecordBuilderTest#buildContractRecordCutsAnOverLengthCrdNumberToTheMasterFieldWidth, #toMasterCrdNumber... | ai/JhomariAtienza2/brv4-dob-default-crd-compare | PASS - confirmed deployed and working: crd_number is truncated to 8 characters on the master record, and a day-3 resend of the same 10-digit CRD no longer produces a spurious change (stable value, no new history row).
DEF-RDMS-BRV4-007 | Blank birth date converted to a garbage sentinel timestamp on the master record, not left blank | TC-BR-459 | BR-459 | Application Defect | Medium | Not Determined | BRv4 dev console, pru_adb_dev | A brand-new producer with WS-DOB blank. | ALLSTATE.LNA.BR-459-CANDIDATE.D20260908.txt | Upload a brand-new producer with a blank date of birth, then read adsi_master.contract_record.birth_date for that subject. | The master record's birth_date field is left blank (NULL), since no real date was ever supplied. | birth_date is populated with an invalid, non-null value: 0000-12-31T17:04:35.000Z - neither a real date nor NULL. The identical value reproduced on a second, independent test (TC-BR-074) with a different blank-DOB producer. | adsi_master.contract_record.birth_date = '0000-12-31T17:04:35.000Z' instead of NULL, reproduced twice. | artifacts/reports/bug-evidence/DEF-RDMS-BRV4-007-BR-459/ (feed file + official ingestion-artifacts + evidence.json); also independently reproduced under TC-BR-074, see artifacts/e2e-brv4/verdicts/TC-BR-074.json | Probable Root Cause - a date-conversion routine appears to compute a spurious value (possibly a timezone-shifted zero/epoch date) instead of checking for and preserving a genuinely absent birth date. | Medium - any producer with no birth date on file gets a corrupted, meaningless value on the master record rather than a clean NULL, which could confuse downstream date-based reporting or filtering. | Confirmed, reproduced independently on 2 separate runs. | None; this is a conversion defect, not something test data can work around. | Confirm with the dev team where in the birth-date conversion path an absent value produces this specific timestamp, and whether the fix is to short-circuit conversion when the source date is blank (mirroring how other date fields on the same record already handle an absent value correctly). | Not a defect – display artifact / by design | Close (BRD clarification) | AdsiMasterRecordBuilder.java:229-246, :652 (BIRTH_DATE_SENTINEL = 0001-01-01) | The SQL dump in the evidence shows contract_record.birth_date = 0001-01-01, not a garbage value. '0000-12-31T17:04:35.000Z' is how the test harness renders DATE 0001-01-01 through a JS/driver timezone conversion (historical LMT offset). The sentinel is deliberate: it was confirmed against a real mainframe ALADSI10 field-diff (2026-08-20), where a blank-DOB producer renders as 1/1/1. The BRD's 'null, never a converted date' step conflicts with that mainframe evidence. In legacy, the person row holds the BR-321 placeholder, so the master record carries it. | Read birth_date as a DATE/string in the harness, not as a JS Date. Update the BR-459 expected result to 0001-01-01 (for persons), and link it to the BR-321 fix (DEF-004). | Unchanged since the last review; verdict stands. | Not a defect | Closed - QA retest PASS | Done | QA / BA | Fix the harness to read DATE columns as text. BA updates BR-459's expected value to 0001-01-01. | No fix needed - not a defect | - | - | - | - | PASS - harness fixed to read the DATE column as text (was misreading it as a JS Date). Confirmed deployed and working: blank DOB now stores the 0001-01-01 placeholder on the master record too, matching DEF-004.
DEF-RDMS-BRV4-008 | Producer with a blank relationship start date is silently dropped entirely, with the run reporting zero records skipped | TC-BR-465 | BR-465 | Application Defect | High | Not Determined | BRv4 dev console, pru_adb_dev | One bundle: one firm + two producers (one with a normal WS-RELN-START-DT, one with it left blank). | ALLSTATE.LNA.BR-465-CANDIDATE.D20260908.txt | Upload one bundle containing a firm and two producers, one of which has a blank relationship start date. | Both producers are created; the one with no start date has its master-record appointment/contract date fields left empty, per the rule. | The producer with the blank start date never appears anywhere - not in pru_adb.contract, not in pru_adb.person, not in adsi_master - despite the ingestion log explicitly reporting '0 record(s) skipped'. | pru_adb.contract has 0 rows for this producer's allstate_id; the run log shows '1 bundle(s) committed, 0 rolled back, 0 record(s) skipped'. | artifacts/reports/bug-evidence/DEF-RDMS-BRV4-008-BR-465/ (feed file + official ingestion-artifacts + evidence.json) | Root cause not yet determined; further developer investigation required. Closely related in symptom to the already-reported DEF-RDMS-BRV4-005 (a second producer under one firm silently dropped) - both show a producer vanishing with no error, warning, or skip signal, though the two may or may not share the same underlying cause. | High - silent, unsignaled data loss: a producer can be entirely absent from the system with the run reporting complete success and zero records skipped. | Confirmed, single run. | None identified. | Dev team review of producer-bundle validation/persistence when WS-RELN-START-DT is blank; check whether this shares a root cause with DEF-RDMS-BRV4-005. | Not a defect – record rejected with F0111 | Close / re-target | FeedRecordValidator.java:591-595 (F0111) | A blank WS-RELN-START-DT is rejected by COBOL rule #71 (1700-VAL-PRODUCER-PROFILE / 4350-VALIDATE-DATE: 'Required, valid date'). LNAERROR in the evidence shows 'F0111 RELATIONSHIP START DATE INVALID ... RECORD REJECTED'. The record was not dropped silently, and this is not the same cause as DEF-005 beyond the misleading skip count. BR-465's null-start case is an HR2 builder rule that can only be reached through a DB seed. The BRD notes the unit test already covers it. | Retest BR-465 by seeding a contract/relationship with a null relationship_start_date and running HR2. Same optional log improvement as DEF-005. | Unchanged since the last review; verdict stands. | Not a defect | Closed - QA retest PASS | Done | QA | The record was rejected with F0111. Re-target TC-BR-465 to an HR2 DB seed with a NULL start date. | No fix needed - not a defect | - | - | - | - | PASS - re-targeted to the DB-seed + HR2-trigger technique (the original feed combination is invalid test data). A DB-seeded NULL start date leaves all three master date fields empty; a real start date populates all three.
DEF-RDMS-BRV4-010 | Producer's home fax number never syncs to the master record | TC-BR-429 | BR-429 | Application Defect | Medium | Not Determined | BRv4 dev console, pru_adb_dev | An existing producer (IP) with a home fax number fed via a standalone D01+D02 update. | ALLSTATE.LNA.BR-429-DAY1/DAY2.D20260908/09.txt | Create a producer, then submit a standalone update carrying a new WS-HOME-FAX-NUM. | adsi_master.contract_record.basic1_home_fax_number reflects the new home fax number, the same way basic1_business_fax_number reflects a firm's business fax (TC-BR-395, confirmed working). | basic1_home_fax_number stays NULL both before and after the update, across every producer sampled (verified directly: all 38 contract_record rows have basic1_present=true, yet every producer row shows basic1_home_fax_number=NULL regardless of the fed value). | adsi_master.contract_record.basic1_home_fax_number = NULL for the test producer both before and after the standalone update; the parallel business-side field (basic1_business_fax_number) does populate correctly for firms. | artifacts/e2e-brv4/verdicts/TC-BR-429.json | Root cause not yet determined - the home-fax mapping for a producer/IP entity appears to be missing or unwired in the basic1 build step, unlike the business-fax mapping for a firm. | Medium - a real, fed value is silently discarded and can never be observed on the master record for producers. | Confirmed, reproduced across 2 independent test runs (initial business-fax attempt found no field at all, second home-fax attempt confirmed NULL both before and after). | None identified. | Confirm with the dev team whether basic1_home_fax_number is supposed to be populated from WS-HOME-FAX-NUM for producer/IP contracts, and if so, locate the missing mapping. | Not a defect - legacy parity (wrong field checked) | Close / re-target | sync/AdsiMasterRecordBuilder.java:470-483 (javadoc) and :673-688 (Basic1Section build); ADSIMSTR.cpy ALL-HOME-FAX-NUMBER (pos 851) | basic1_home_fax_number is null on purpose. Legacy UTP27801 never MOVEs ALL-HOME-FAX-NUMBER anywhere, so on the mainframe it is always blank too. For an IP, the producer's HOME fax lands in basic1_BUSINESS_fax_number instead. That is a legacy shared-working-storage quirk: 5500-BUILD-BASIC1-SECTION-PARA (UTP27801:1311-1318) reads DCLUTT-ALL-ADDR after the home-address fetch has overwritten it. It was confirmed by the 2026-08-20 mainframe-vs-Java ALADSI10 field-diff, and the builder reproduces it. BR-429 itself is about BUSINESS fax change detection, not home fax. | Re-target TC-BR-429: Day 1 create the IP, Day 2 send a standalone D01+D02 with a new WS-HOME-FAX-NUM. Expect contract_record.basic1_business_fax_number = the new home fax, and the HR2 activity record to flag the business-fax change. basic1_home_fax_number stays NULL (parity). Optionally ask the BA to add a note to BR-429 explaining the IP quirk. | Unchanged since the last review; verdict stands. | Not a defect | Closed - QA retest PASS | Done | QA | Legacy parity. For an IP, the home fax lands in basic1_business_fax_number. Retest TC-BR-429 against that field. | No fix needed - not a defect | - | - | - | - | PASS - retested against the corrected master column (basic1_business_fax_number, not basic1_home_fax_number as QA first guessed).
DEF-RDMS-BRV4-011 | A byte-identical resubmission is not treated as a no-op - it still stamps updt_ts and writes new history/activity rows | TC-BR-051, TC-BR-319, TC-BR-318 | BR-051, BR-319, BR-318 | Application Defect | Medium | Not Determined | BRv4 dev console, pru_adb_dev | An existing firm or producer, resubmitted via a standalone update carrying EXACTLY the same field values as its prior state. | ALLSTATE.LNA.BR-051/BR-319/BR-318-DAY2/DAY3 (byte-identical resubmissions) | Submit a standalone update whose D01/D02 (or C) record is byte-identical to what is already on file. | Per these rules' own text, a resubmission that changes nothing should be a no-op: no new pru_adb.contract.updt_ts stamp, no new pru_adb.contract_history/activity_log_entry row. | Confirmed on 3 independent entities (a producer via TC-BR-051, a different producer via TC-BR-319, and a firm via TC-BR-318): each byte-identical resubmission still stamped updt_ts and added a new history/activity row, exactly as if a real change had occurred. | contract.updt_ts moved from NULL to a real timestamp, and contract_history/activity_log_entry gained a new row, on a resubmission with no actual field difference from the prior state - reproduced 3 times across 2 entity types. | artifacts/e2e-brv4/verdicts/TC-BR-051.json, TC-BR-319.json, TC-BR-318.json | Root cause not yet determined - the change-detection/no-op path this rule set describes does not appear to gate the write for a resubmission via the standalone-update route, even though HR2's own detectChanges log line correctly reports "N of M extract entries unchanged" for other purposes. | Medium - byte-identical resubmissions inflate history/activity tables and produce misleading "this record changed" signals downstream, even though nothing did. | Confirmed, reproduced independently 3 times (2 different producers, 1 firm). | None identified. | Confirm with the dev team whether the standalone-update ingestion path is expected to compare against the prior committed state before writing history/activity rows, the way the rules describe. | Valid defect - CONFIRMED against UTP27201 source | Open - dev fix | ingestion/ProducerAppointmentServiceImpl.java updateFirm (:429-540), updateProducer (:899-950), upsertRelationship (:1326-1391) | COBOL (ADSI_Allstate_POC/SRC/UTP27201.txt, 3140-UPDATE-PROFILE-INFO :1384-1541) gates EVERY write on an actual difference: - Contract history (8200-INSERT-CNTRHT, UTT_ALL_CNTR_HT) is performed only inside 8100-COMPARE-CNTR-INFO's IF, when RES-ST / FIRM-TYPE-CD (firm) or RES-ST / PROD-ROLE-CD / EXT-AGT-ID (producer) differ (:1603, :1624). - The contract UPDATE with UPDT_TS (8300) runs only IF WS-CNTR-DETAILS-CHNGD = 'Y' (:1388). - The MI00MI activity row runs only IF WS-INSERT-ACTIVITY = 'Y' (:1486). That flag is set only by a successful history/contract/firm/person/address write. - Node-rel history (3163) and the node-rel update (3164) run only when start/end date or status differ (:2481-2490, :1510), and the relationship activity row only IF WS-INSERT-ACTIVITY1 = 'Y' (:1520). Java writes contract_history, stamps updt_ts, writes node_relationship history/update, and writes the activity row unconditionally. So all three symptoms in the ticket are real parity gaps. HR2/master output is unaffected (it compares and finds no change), but ADB history/activity tables diverge from legacy. | Dev fix: in updateFirm/updateProducer, write ContractHistory + save the contract only when the contract FieldDiff is non-empty. In upsertRelationship, write history + update only when relationshipChanged. Call writeActivity for MI00MI only when (contract ¦¦ firm/person ¦¦ address) changed, and for the relationship code only when relationshipChanged. Note that legacy can write TWO activity rows on one update (MI00MI + RA/TE/MI) - mirror that. Re-run the Day 1-6 parity corpus. QA retest: a byte-identical resend -> no new contract_history / node_relationship_history / activity_log_entry row, and updt_ts unchanged. | COBOL check 2026-09-30 (actual source, ADSI_Allstate_POC/SRC): see Code Analysis. | Valid defect | Fixed - PASS for TC-BR-051/318; TC-BR-319 to re-target | Re-target TC-BR-319 | Dev -> QA | Apply brv4-fixes patch. History, updt_ts, node-rel history/update, person/firm updates and activity rows are now written only on a real change, and two activity rows (MI00MI + relationship code) when both change (UTP27201 3140). Tests: ...#aByteIdenticalResendWritesNoHistoryNoActivityAndNoUpdateStamp, ...#anUpdateChangingTheContractAndTheRelationshipWritesBothActivityRows. QA: byte-identical resend -> no new rows. | Fixed - on branch, not yet committed | History, updt_ts, firm/person updates, node-rel history/update and activity rows are written only on a real change. Two activity rows (MI00MI + relationship code) when both change (UTP27201 3140 :1388/:1486/:1520). | ProducerAppointmentServiceImpl (updateFirm, updateProducer, upsertRelationship, applyPersonDetails, writeActivity, AddressChangeKind.INSERTED); ProducerAppointmentSqlFailureTest (2 tests adjusted) | ProducerAppointmentServiceIT#aByteIdenticalResendWritesNoHistoryNoActivityAndNoUpdateStamp, #anUpdateChangingTheContractAndTheRelationshipWritesBothActivityRows | ai/JhomariAtienza2/brv4-dob-default-crd-compare | TC-BR-051 and TC-BR-318 PASS (confirmed deployed: byte-identical resend is now a true no-op - no updt_ts stamp, no new row). TC-BR-319 could NOT be confirmed - see DEF-RDMS-BRV4-016 (contract_history shows zero rows for ANY change right now, real or no-op, so this specific TC cannot distinguish "no-op correctly skipped" from "writes broken entirely"). | TC-BR-319 used the wrong trigger. BR-319's own test step is to change a CONTRACT attribute (resident_state / producer_role_code / external id). A middle-name change is a PERSON field and never writes contract_history in legacy (8100 compares only RES-ST/PROD-ROLE-CD/EXT-AGT-ID). Re-target TC-BR-319 to a resident-state change and expect contract_history +1. Reproduced 2026-10-01: a resident-state change gives contract_history 0 -> 1 and stamps updt_ts.
DEF-RDMS-BRV4-012 | Blanking the date of birth on an EXISTING producer wipes a previously-correct value to NULL | TC-BR-322 | BR-322 | Application Defect | Medium | Not Determined | BRv4 dev console, pru_adb_dev | An existing producer with a real, previously-fed date of birth. | ALLSTATE.LNA.BR-322-DAY1/DAY2.D20260908/09.txt | Submit a standalone D01+D02 update for this producer with WS-DOB left blank. | A blank WS-DOB on an update to an EXISTING record is ignored, leaving the previously-correct birth_date in pru_adb.person untouched (consistent with how other fields on this app appear to treat a blank input as "no change" rather than "clear this field"). | pru_adb.person.birth_date, which held a real date (1975-06-14) before the update, was overwritten to NULL after a standalone update carrying a blank WS-DOB. | pru_adb.person.birth_date = NULL after the update, versus a real, previously-correct date before it. | artifacts/e2e-brv4/verdicts/TC-BR-322.json | Probable root cause - related to the same blank-DOB family of issues already confirmed for NEW producers (DEF-RDMS-BRV4-004, DEF-RDMS-BRV4-007): a blank date-of-birth input appears to be converted to an explicit NULL/clear instruction rather than being treated as "field not supplied, leave as-is". | Medium - a single blank field on a routine update can silently destroy a previously-correct, real date of birth with no error or warning. | Confirmed, single run. | None identified. | Confirm with the dev team whether a blank WS-DOB on an update to an existing record is meant to clear the stored date, and if not, whether the fix should mirror how other blank fields on this same update path are already handled as "leave unchanged". | Valid - duplicate of DEF-004 (update path, BR-322); already fixed on branch | Merge into DEF-004; correct the expected result | ingestion/ProducerAppointmentServiceImpl.java applyPersonDetails (:2074) -> birthDateOf(profile) on branch ai/JhomariAtienza2/brv4-dob-default-crd-compare | Confirmed: today a blank WS-DOB on an update wipes the stored DOB to NULL. But the expected result in this ticket ('leave the old date untouched') contradicts the BRD and the COBOL. BR-322: 'the same placeholder date is applied as when the person is created ... It must not be left at the previously stored date, and must not be nulled.' 5142-COMPARE-PERS-INFO-PARA :4094 defaults WS-DOB spaces to '0001-01-01' (Validation Review UTP27201 #34). The fix on the branch stores 0001-01-01. It is covered by ProducerAppointmentServiceIT#anExistingPersonPresentedWithABlankDateOfBirthGetsThePlaceholderNotNull, which fails on the old code and passes with the fix. | Close as a duplicate of DEF-004. Retest after the branch merges: existing producer with DOB 1975-06-14, then a standalone update with blank WS-DOB -> person.birth_date = 0001-01-01 (read as text). Note for the BA request on DEF-004(b): BR-322 already answers the update-path question (placeholder, not 'keep'). If the business wants 'keep', that is a deliberate BRD change. | Unchanged. Duplicate of DEF-004; fixed on the branch. The expected result should be 0001-01-01 (BR-322), not 'keep the old date'. | Valid defect (duplicate) | Fixed - QA retest PASS (deployed) | Done | QA | Retest with DEF-004 after merge. Expected: 0001-01-01 (BR-322), not the old date. | Fixed - on branch, QA-verified PASS (same fix as DEF-004) | A blank WS-DOB on an update stores 0001-01-01 instead of wiping the DOB to NULL (UTP27201 5142 :4094, BR-322). | ProducerAppointmentServiceImpl (applyPersonDetails -> birthDateOf) | ProducerAppointmentServiceIT#anExistingPersonPresentedWithABlankDateOfBirthGetsThePlaceholderNotNull | ai/JhomariAtienza2/brv4-dob-default-crd-compare | PASS - confirmed deployed and working: blank DOB on an EXISTING producer now stores 0001-01-01 (not the old date, not NULL - QA's own original expectation of "leave the old date" was wrong and has been corrected).
DEF-RDMS-BRV4-013 | HR2's daily sync run has no fault isolation - one node that fails to build crashes the WHOLE day's sync, silently blocking every other legitimate change that cycle | TC-BR-478, TC-BR-482, TC-BR-081, TC-BR-428 | BR-478, BR-482, BR-081, BR-428 | Application Defect | High | Not Determined | BRv4 dev console, pru_adb_dev | A contract/organization node that AdsiMasterRecordBuilder cannot build (e.g. a contract whose subject_id has no matching person row) exists in the working set for a given cycle date, alongside other, unrelated, perfectly valid firms/producers changing that same day. | Directly observed via TC-BR-478's own precondition (a contract with no matching person, node_id 900000067980) left uncleaned in the DB from an earlier test run. | Run any cycle for a feed date where one node in the day's working set cannot be built by AdsiMasterRecordBuilder (e.g. a contract with no matching person), alongside other, unrelated, valid firms. | The one bad node is skipped/logged (as the app itself does log: "Skipped node <id> ... could not build a record ... No person found for subject id <id>"), and every other valid node in that cycle still syncs normally to adsi_master. | The single bad node's WARN-level skip is followed immediately by "ERROR HR2 sync run for feed date <date> failed" - the entire day's HR2 sync run aborts. adsi_master.organization_record/contract_record for every OTHER, perfectly valid firm/producer processed that same cycle also never gets written, with no error surfaced anywhere pointing at those unrelated, valid entities - they simply appear to silently fail their own, unrelated test expectations. | Confirmed by direct app log capture: the single log excerpt 'WARN Skipped node 900000067980 (CONTRACT) - AdsiMasterRecordBuilder could not build a record - legacy D003 - No person found for subject id 900000067980' immediately followed by 'ERROR HR2 sync run for feed date 2026-09-08 failed'; and reproduced/confirmed by observing TC-BR-482, TC-BR-081 and TC-BR-428 (three completely unrelated firms/producers, three different test cases) all fail identically with "no master row written" while this one poison row sat in the DB, then all three PASS cleanly once the single poison row was removed. | artifacts/e2e-brv4/verdicts/TC-BR-478.json (root-cause evidence), TC-BR-482.json, TC-BR-081.json, TC-BR-428.json (all show the downstream symptom and its resolution) | Confirmed Root Cause - AdsiMasterRecordBuilder throws an uncaught exception when it cannot build a record for a node in the day's working set (e.g. missing person), and this exception is not caught/isolated per-node by the calling HR2 sync-run orchestration - it propagates up and aborts the entire cycle's sync run for every node, not just the one that failed. | High - a single malformed or orphaned record (which could arise from many real-world causes, not just this test suite's own leftover data) silently blocks the ENTIRE day's master-file sync for every other firm and producer processed that cycle, with no error pointing at the actually-unrelated, valid records that also failed to sync as a result. This is a significant blast-radius/reliability gap: one bad row can silently corrupt an entire day's downstream reporting for a firm with many otherwise-unrelated changes. | Confirmed - directly triggered this on 2026-09-28 by leaving TC-BR-478's own precondition (a contract with no matching person) in the DB and observing 3 unrelated TCs (BR-482, BR-081, BR-428) all fail with "no master row written" simultaneously, then all pass again once that single row was removed. | None from a test-data perspective (this suite now cleans up its own equivalent poison rows in a finally block) - but no workaround exists in production for a REAL orphaned/malformed record that could arise from an actual data-integrity issue upstream. | Confirm with the dev team whether AdsiChangeDetectionService/the HR2 sync-run orchestration is expected to catch and skip a per-node build failure (matching the WARN-level 'Skipped node' log line's own apparent intent), rather than letting the exception propagate and abort the whole cycle's sync run; this also means every other confirmed defect in this report that was found via a full-cycle HR2 sync could theoretically be masked or produce a false negative on any day a single unrelated bad record exists in the working set. | Not as described - confirmed end-to-end: the crash is caused by the 12-digit test node id; per-node isolation works | Close (test data); optional Low hardening | shared/export/ErrorArtifactExportService.java:204-208 packNodeId; sync/AdsiChangeDetectionService.java:114-170; ingestion/trigger/FeedIngestionLauncher.java:217-222 | The revised ticket repeats the same root-cause claim, but it is not supported by the code or by a rerun. The builder does not throw. A contract with no person comes back as a D003 skip (the WARN line QA captured) and the loop continues. The run aborts afterwards, when that D003 entry is written to the fixed-width ERRFILE: NODE-ID is S9(11) COMP-3, and packNodeId throws IllegalArgumentException for any id above 99,999,999,999. The seeded poison id 900000067980 has 12 digits. END-TO-END REPRO (2026-09-30, real Spring context + PostgreSQL 16, HrMasterSyncRunner.run(2026-09-08)): (a) orphan contract with node id 900000067980 -> same WARN 'Skipped node 900000067980 ... No person found', then the run throws; root cause IllegalArgumentException 'ERRFILE NODE-ID must be a non-negative 11-digit value'. (b) identical orphan with node id 90000067980 (11 digits) -> same WARN skip, the run COMPLETES and marks the day's activity processed. So one orphaned record with a real-sized id does NOT block the day's sync. | QA: reseed the TC-BR-478 precondition with a node id of 11 digits or fewer and rerun TC-BR-478/482/081/428 together. Expected: a D003 row in errfile-detectchanges and all other nodes synced. Capture the full stack trace after 'HR2 sync run ... failed' (FeedIngestionLauncher logs it). Dev (optional, Low): make the ERRFILE writer degrade gracefully for an unrepresentable id, or add a DB check that node_id <= 99999999999. | Ticket text revised but the claim is the same. Re-verified with an end-to-end repro: not a fault-isolation defect. | Not a defect (test data) | Closed - retracted by QA | Done | QA (optional Dev hardening) | Reseed the orphan with a node id of 11 digits or fewer and rerun TC-BR-478/482/081/428 together. Optional Low ticket: the ERRFILE writer should not abort HR2 for an oversized id. | No fix needed - test data (optional Low hardening) | - | - | - | - | RETRACTED by QA - confirmed dev's "not a defect, test data" verdict. Reseeded the orphan with an 11-digit node/subject id (was 12 digits). The app now gracefully skips the unbuildable node (logged as a normal "build failure", detectChanges' own skip-count categorises it correctly) with NO crash, and all 3 previously-affected sibling TCs (BR-482/081/428) now pass cleanly in the same cycle. QA's own DEF-RDMS-BRV4-013 report is withdrawn. | Agreed: closed (retracted by QA).
DEF-RDMS-BRV4-014 | A standalone address update clears line2/phone/fax to blank instead of preserving the prior value, contradicting the documented conditional-field rule | TC-BR-088 | BR-088 | Application Defect | Medium | Not Determined | BRv4 dev console, pru_adb_dev | An existing firm with a full business address on file (line1, line2, city, state, zip, phone, fax all populated). | ALLSTATE.LNA.BR-088-DAY1/DAY2.D20260908/09.txt - day2 is a standalone C-only update changing line1/city/state/zip to new values while sending line2/phone/fax blank. | Submit a standalone C-only update for an existing firm where line1/city/state/zip carry new values and line2/phone/fax are sent blank. | Per the rule's own text, line1/city/state/zip are carried unconditionally (always moved), but line2/phone/fax are moved only where neither blank nor absent - so a blank line2/phone/fax on the update should leave the prior, already-stored values untouched rather than clearing them. | line1/city/state/zip correctly updated to their new values, but line2/phone/fax were all cleared to empty string - the prior values (day1's "SUITE 1" / phone / fax) were overwritten to blank rather than preserved. | pru_adb.address (BUSINESS row for this contract): line2="" (was "SUITE 1"), phone_number="" (was "3125551000"), fax_number="" (was "3125552000") after an update that sent all three blank - line1/city/state/zip correctly show the new day2 values. | artifacts/e2e-brv4/verdicts/TC-BR-088.json | Probable root cause - the address block appears to be written as a wholesale field-for-field overwrite (every incoming field value replaces the stored one, blank or not) rather than the field-by-field conditional move the rule describes, where a blank line2/phone/fax should be a no-op on that specific field. | Medium - any address update that omits the optional line2/phone/fax fields (a very plausible partner-side scenario) silently destroys previously-good data on those fields, with no error or warning. | Confirmed, single run, using the standalone-update route (the only route available for an update to an already-existing firm in this environment). | None identified. | Confirm with the dev team whether the address-maintenance code path is expected to skip blank/absent line2, phone and fax on an update (matching the documented rule), or whether the current wholesale-overwrite behavior is the intended, updated design. | Not a defect - CONFIRMED against UTP27201/UTP27801 source; BRD BR-088 misdescribes legacy | Close; BA to reword BR-088 | ingestion/ProducerAppointmentServiceImpl.java upsertAddress (:1236-1300); sync/AdsiMasterRecordBuilder.java toContractAddress (:913-922) | (1) HR1 / pru_adb.address: UTP27201 3152-COMPARE-ADDRTYP-A-PARA (:1938+) compares LINE-2, PH-NUM and FAX-NUM field by field and MOVEs the incoming value when it differs, blank included. So legacy also clears line2/phone/fax, and Java matches. (2) HR2 / master record: UTP27801 does MOVE line2/phone/fax only 'IF ... NOT = SPACES AND LOW-VALUES' (:1167, :1181, :1312). BUT the record it moves into (LK-ADSI-MASTER-CNTR-RECORD, passed from UTP27901 :2604) is NOT re-initialised per call: 1100-INIT-CURSOR-VARS (:556) initialises only the key section and FILLER-00, and only LINE-3 is spaced (:1159). So a blank line2/phone does not 'keep what the master already shows' for that subject. It keeps whatever the PREVIOUS node built in the same run left there: a cross-record carry-over, not a rule. BR-088's wording is a misreading of that. Java writes the subject's own (blank) value, which is the correct intent. Reproducing the carry-over would reproduce a legacy bug (same reasoning as decision D7). | Close. BA: reword BR-088 to 'line2/phone/fax are moved only when present; legacy does not reset the output area between records' (the documented quirk), and mark it as not reproduced. QA: optional regression on adsi_master.contract_record - after the blank update, business_address_line2 / business_telephone_number are blank, not the prior values. If a mainframe comparison ever shows a neighbouring record's line2/phone carried over, log it as a known legacy artefact. | COBOL check 2026-09-30 (actual source, ADSI_Allstate_POC/SRC): see Code Analysis. | Not a defect | Closed - QA retest PASS | Done | BA / QA | COBOL confirms HR1 parity, and that BR-088 describes a legacy carry-over quirk, not a rule. BA rewords BR-088. | No fix needed - not a defect (BA to reword BR-088) | - | - | - | - | PASS - confirmed not a defect, matches legacy COBOL parity per dev's analysis. TC-BR-088 updated to assert the confirmed-correct (legacy-matching) behaviour instead of flagging it as a gap.
DEF-RDMS-BRV4-009 | A no-change update deletes a producer's blank HOME address row (dev-raised; COBOL-confirmed) | TC-BR-140 (Day 3) | BR-140 / BR-324 | Application Defect | Low | Not Determined | BRv4 dev console, pru_adb_dev | An existing producer that already has a blank HOME row (e.g. inserted by an earlier update with a blank home address). |  | Send a standalone update for that producer with the home address still fully blank. | Nothing changes, so the blank HOME row stays (legacy deletes only when found AND changed). | From code review: Java deletes the HOME row whenever one is on file and the incoming line 1 is blank, even if nothing differs. |  |  | Confirmed against UTP27201.txt 3150-ADDRTYPE-A-PROCESS-PARA (:1545-1572): 3155-DELETE-ADDRESS-PARA is performed only inside IF WS-ADDR-DETAILS-CHNGD = 'Y', which 3152-COMPARE-ADDRTYP-A-PARA sets only when some field differs. ProducerAppointmentServiceImpl.applyProducerAddresses (:1122-1126) calls addressRepository.delete with no change check. | The HOME row flips between present and absent on successive cycles, which changes the ALADSI10 site-type (UTP27801 home fetch) and breaks parity with the mainframe. | Code/COBOL confirmed; QA repro pending. | None. |  | Valid defect - CONFIRMED against UTP27201 source | Open - dev fix | ingestion/ProducerAppointmentServiceImpl.java applyProducerAddresses (:1110-1140) | Legacy deletes only when the row is found AND changed (:1549-1566). Java deletes on found alone. The fix is one condition: delete only when the incoming block differs from the stored row (same equalOrBothBlank compare upsertAddress uses). | Dev: add the compare before the delete; add an IT (blank HOME row on file + blank update -> row kept). QA: add a Day 3 step to TC-BR-140. | Re-added 2026-09-30: dropped from QA's list, but the COBOL confirms it. | Valid defect | Fixed - awaiting QA 3-day TC-BR-140 retest | Yes - 3-day TC-BR-140 | Dev -> QA | Apply brv4-fixes patch. The delete now happens only when the stored HOME row differs from the incoming block (UTP27201 3150 :1545-1572). Test: ProducerAppointmentServiceIT#aBlankHomeRowOnFileSurvivesAnUnchangedBlankResend. QA: 3-day TC-BR-140. | Fixed - on branch, not yet committed | The blank HOME row is deleted only when it differs from the incoming block (UTP27201 3150 :1545-1572). | ProducerAppointmentServiceImpl (applyProducerAddresses, nonEmailFieldsDiffer) | ProducerAppointmentServiceIT#aBlankHomeRowOnFileSurvivesAnUnchangedBlankResend | ai/JhomariAtienza2/brv4-dob-default-crd-compare | Could not be independently confirmed this round - see DEF-RDMS-BRV4-016 (a broader regression means no history/address writes are currently observed for ANY genuine change in this environment, masking whether this specific fix landed correctly). | Retest with the 3-day TC-BR-140 scenario (DEF-016 is not a real blocker, see its row). Reproduced 2026-10-01: the day-2 blank update inserts the empty HOME row, and the fix keeps it on an unchanged resend (ProducerAppointmentServiceIT#aBlankHomeRowOnFileSurvivesAnUnchangedBlankResend).
DEF-RDMS-BRV4-015 | A blank correspondence address on the first BD firm does not reject the bundle (B0608 not enforced) | TC-BR-016 | BR-016, BR-185 | Application Defect | Medium | Not Determined | BRv4 dev console, pru_adb_dev | A bundle whose first BD firm record has WS-CORRES-ADD-L1 (and city/zip) blank. | ALLSTATE.LNA.BR-016-CANDIDATE.D20260908.txt (blank correspondence address, invalid resident state, and a valid control bundle in one file) | Submit a bundle where the first BD firm's correspondence address is entirely blank (WS-CORRES-ADD-L1 = SPACES). | Per the BRD (BR-185/B0608: "IF WS-CORRES-ADD-L1 = SPACES ... MOVE 'B0608' TO WS-ERROR-CODE"), the record should be refused and the whole bundle rejected - no organisation row created. | An organisation row WAS created despite the blank correspondence address (count=1), and no B0608 line appears in the run log. The SAME run correctly rejected a sibling first-firm validation (B0606, invalid resident state 'ZZ' - count=0) and still committed a valid control bundle normally, ruling out a test-construction issue or a whole-run failure. | pru_adb.organization has a row for the blank-correspondence-address BD; no B0608 anywhere in the run log. | artifacts/e2e-brv4/verdicts/TC-BR-016.json | Not yet determined by dev - QA's working theory: the B0608 branch of 1510-VAL-FIRST-FIRM (correspondence-address completeness) was not carried over into the modernised HR1 validation, while the B0606 branch (resident-state) clearly was. | Medium - a first BD firm with a malformed/missing correspondence address is silently accepted instead of refused. | Confirmed, single run, cross-checked against a working sibling validation (B0606) in the same run. | None identified. | Confirm with the dev team whether BR-185/B0608 was ported into the modernised first-firm validation. | Not a defect - QA's exact feed rejected with B0608 (verified end to end) | Close; fix TC-BR-016 assertion/test data |  |  |  |  | Not a defect | Closed - confirmed via corrected TC | Yes - assert on LNAERROR, fresh BD id | QA | Assert B0608 in lnaerror-<date>.txt; use a fresh BD id or a clean DB; check the existing org row's crt_ts. | No fix needed - not a defect (verified with QA's feed) | [5 empty] | NOT A DEFECT - re-verified 2026-10-01 with QA's EXACT evidence feed (ALLSTATE.LNA.BR-016-CANDIDATE.D20260908.txt) run end to end on the deployed code (FeedIngestionLauncher -> PostgreSQL). Result: lnaerror-20260908.txt holds 'A995013000 ... B0608 "CORRESPONDENCE ADDRESS" INVALID IN THE FIRST "FIRM ENTITY" (BD) RECORD. BD FIRM BUNDLE REJECTED' and 'A995013100 ... B0606'. The only organisation created is the control bundle's (E2E BRV4 BD50132 LLC). The blank-correspondence BD gets NO organisation row. Why QA saw count=1: (1) the 'B0608 log line' check is not valid evidence - error codes are written to LNAERROR (File 3), never to the run log, which is why the B0606 check ALSO shows '(none found)' while passing. (2) The org count comes from orgCodeForBd() -> org_code, run at generation 99 of this TC against a non-clean DB. An organisation left for A995013000 by an earlier generation of TC-BR-016 (when it tested the blank resident state, which is accepted - DEF-001) would match. Check that row's crt_ts: it will pre-date the 2026-09-30T02:15 run. Action: assert on lnaerror-<date>.txt (File 3) for B0608, and use a fresh BD Allstate id per run (or clean the DB / filter the organisation by crt_ts in the run window).
DEF-RDMS-BRV4-016 | contract_history, node_relationship_history and address-on-create writes appear to not fire at all for a genuine change, not just for no-ops - likely an over-broad side effect of the DEF-RDMS-BRV4-011 fix | TC-BR-050, TC-BR-319, TC-BR-140 | BR-050, BR-319, BR-140, BR-324 | Application Defect | High | Not Determined | BRv4 dev console, pru_adb_dev (freshly cleaned 2026-09-30) | A brand-new producer created via a normal feed bundle, then a genuine, unrelated field change (e.g. WS-MIDDLE-NAME) submitted as a standalone update; separately, a brand-new producer with an entirely blank HOME address block. | TC-BR-050 (unmodified, previously-passing test), TC-BR-319 (day2 middle-name change), TC-BR-140 (day1 blank HOME address on a new record) | Create a producer, then submit a standalone update changing one field. Separately, create a producer whose HOME address block is entirely blank. | A genuine field change should write a new pru_adb.contract_history row and a pru_adb.node_relationship_history row (BR-050, previously a passing, established behaviour); a brand-new record with a blank HOME address should still get a HOME address row inserted (BR-140, also previously passing). | TC-BR-050 (re-run UNMODIFIED, not edited by QA this round) now fails: chBefore=0, chAfter=0, nrhBefore=0, nrhAfter=0 - no history row at all for a genuine change. pru_adb.contract_history has ZERO rows total across the whole database. TC-BR-319 (a different trigger field, confirmed-valid node_id) shows the identical zero-count pattern. TC-BR-140 shows a brand-new producer's blank HOME address produces NO address row of any type (not just a missing HOME-typed row). | pru_adb.contract_history: 0 rows total in the database. pru_adb.address: no row at all for a freshly-created producer with a blank HOME address block. | artifacts/e2e-brv4/verdicts/TC-BR-050.json, TC-BR-319.json, TC-BR-140.json | Probable root cause - DEF-RDMS-BRV4-011's fix ("history, updt_ts, ... written only on a real change") touches ProducerAppointmentServiceImpl.updateFirm/updateProducer/upsertRelationship/applyPersonDetails/writeActivity/AddressChangeKind.INSERTED - the "is this a real change" gate appears to be suppressing writes universally, not just for byte-identical resends. | High - if confirmed, this silently breaks history/audit-trail writes and initial address population for EVERY producer, not a narrow edge case. | Confirmed, reproduced independently across 3 different TCs (one unmodified) using 2 different trigger fields, in a freshly-cleaned environment where DEF-RDMS-BRV4-011's fix is confirmed deployed. | None identified. | Urgent: confirm with the dev team whether the DEF-RDMS-BRV4-011 fix's change-detection gate is correctly detecting a real change at all in the currently deployed build - the evidence points to it never detecting one. | Not a defect - test expectations do not match COBOL (reproduced) | Close; re-target TC-BR-050/319/140 |  |  |  |  | Not a defect | Closed - confirmed via corrected TC | Yes - re-targeted TC | QA | Use contract-attribute and relationship triggers for the history checks; query the BUSINESS address by contract number. | No fix needed - not a defect |  |  |  |  | CONFIRMED, isolated recheck 2026-09-30 on a freshly cleaned DB, ruling out both stale data and the concurrent test activity observed earlier: TC-BR-050 run ALONE (no other tests running) still shows chBefore=0 chAfter=0 nrhBefore=0 nrhAfter=0 for a genuine field change. TC-BR-140 run ALONE the same way shows the producer contract IS created (contractFound=1) but zero address rows of any kind exist for it (allAddrForSsn=[]). Filing as a confirmed bug. | NOT A DEFECT - the expected results do not match the COBOL. Reproduced QA's scenarios end to end on the deployed code (real feeds through FeedIngestionLauncher, PostgreSQL, 2026-10-01): - Day 1, create with a blank home: AP00AP; address rows = [BUSINESS:<contract no>], no HOME row (correct, UTP27201 :3092). - Day 2, middle-name change only: person updated, MI00MI activity written, contract_history 0, node_rel_history 0 (correct: 8100 writes UTT_ALL_CNTR_HT only for RES-ST / PROD-ROLE-CD / EXT-AGT-ID, and 3163 only for relationship dates/status). The empty HOME row is now inserted (BR-140 update path). - Day 3, resident-state change: contract_history 0 -> 1, updt_ts stamped, MI00MI. - Day 4, status T: node_rel_history 0 -> 1, TE00TE. So history IS written for real contract/relationship changes. TC-BR-050 and TC-BR-319 used person-field triggers, which never write contract/relationship history in legacy. They passed before only because pre-fix Java wrote history on EVERY update (exactly DEF-011). 'contract_history has 0 rows in the DB' is expected when no test has changed a contract attribute. TC-BR-140 queried addresses by SSN; the BUSINESS row is keyed by contract number. Action: re-target TC-BR-050/319 to a resident_state or producer_role change (contract_history +1) and a relationship date/status change (node_relationship_history +1). For TC-BR-140, query the BUSINESS row by contract number and expect no HOME row on day 1.
DEF-RDMS-BRV4-017 | A standalone BD update that blanks the whole correspondence (mailing) address is reported as a BD contract update but never changes or removes the MAILING address row, so the master record keeps its ALT_ADDRESS section | TC-BR-436 | BR-436 | Application Defect | Medium | Not Determined | BRv4 dev console, pru_adb_dev (run 2026-10-01, HR2 auto-chained and COMPLETED for both days) | A Broker-Dealer already committed to ADB and the ADSI master with both a BUSINESS and a MAILING address (day1 bundle A+B+C, COMPLETED; master basic4_sections = [MISC, ALT_ADDRESS, ADDITIONAL_INFO]). | Day1 ALLSTATE.LNA.BR-436-DAY1.D20260908.txt (A+B+C, baseline BD A995125000 / contract A97N4N). Day2 ALLSTATE.LNA.BR-436-DAY2.D20260909.txt (A + standalone C, byte-verified: WS-CORRES-ADD-L1/L2/CITY/ST-CD/ZIP-CD/PH-NUM/FAX-NUM/EMAIL (cols 307-498) all spaces; every other field identical to day1). | 1. Upload day1 bundle for feed date 2026-09-08 and let HR1+HR2 complete. 2. Confirm pru_adb.address holds a MAILING row (PO BOX 1000) and adsi_master.contract_record.basic4_sections has 3 elements incl. ALT_ADDRESS. 3. Upload day2 standalone C for 2026-09-09 that blanks the entire correspondence block. 4. Re-query pru_adb.address, pru_adb.contract.updt_ts, pru_adb.activity_log_entry and adsi_master.contract_record.basic4_sections. | The incoming correspondence block differs from the stored MAILING row, so HR1 processes it (BR-325 field-by-field compare; BR-088/DEF-014: line1/city/state/zip carried unconditionally, blank included) - the MAILING row is removed (legacy delete-when-changed path, UTP27201 3150/3155) or at minimum blanked. HR2 then rebuilds the BD without the postal section: basic4_sections drops 3 -> 2, ALT_ADDRESS gone, internal structure marked changed (BR-436) and an activity record written. | Day2 COMPLETED with no LNAERROR/ADBSKIP/ADBERROR entries and CNTLRPT reports NUMBER OF BD CONTRACTS UPDATED IN ADB = 1, but nothing was persisted: MAILING row still PO BOX 1000 with updt_ts null, contract updt_ts null, no day2 activity row. HR2: detectChanges 76/76 unchanged, 0 changes applied; basic4_sections still 3 [MISC, ALT_ADDRESS, ADDITIONAL_INFO]. | pru_adb.address (A97N4N, MAILING): line1=PO BOX 1000, city=SAMPLETON, updt_ts=null. pru_adb.contract (A995125000, node 75122): updt_ts=null. pru_adb.activity_log_entry (A97N4N): 1 row, AP00AP from day1 only. adsi_master.contract_record (97N4N): basic4_sections ALT_ADDRESS addressLine1=PO BOX 1000. | artifacts/reports/bug-evidence/DEF-RDMS-BRV4-017-BR-436/ (day1+day2 feeds, official day2 ingestion-artifacts ZIP + extracted CNTLRPT/LNAERROR/ADBSKIP/ADBERROR, console error-context, screenshot, verdict JSON, DB-Evidence.txt) | [Superseded by dev triage 2026-10-05 - see Code Analysis] Probable root cause - the firm correspondence-address branch of HR1 short-circuits when the incoming block is entirely blank (treats it as "no mailing address supplied" rather than comparing it to the stored row), while still incrementing the BD-contracts-updated counter. The equivalent BUSINESS-address path compares and overwrites correctly (TC-BR-325/053/088 pass in the same run), and the producer HOME path was fixed to delete only when changed (DEF-RDMS-BRV4-009), so the firm MAILING path appears to be missing the same compare/delete handling. | A BD can never lose its postal address through the feed: ADB and the ADSI master keep a stale mailing address indefinitely, downstream receives an outdated ALT_ADDRESS section, and the BR-436 structure-change mark / activity record is never produced. The control report also overstates updates (1 counted, 0 applied), which hides the problem from operations. | Confirmed, single run (deterministic - same feed bytes; all-blank block vs populated stored row). | None via the feed. Manual DB correction of pru_adb.address only. | 1. Compare the firm (BD) correspondence-address handling in the HR1 ingestion service against UTP27201 3150-ADDRTYPE-*-PROCESS / 3155-DELETE-ADDRESS-PARA for the correspondence type: does legacy delete/blank the MAILING row when the incoming block is all spaces and differs from the stored row? 2. Check whether an all-blank-block guard skips the address before the compare. 3. Make the CNTLRPT "BD CONTRACTS UPDATED" counter reflect persisted changes only. 4. If legacy genuinely ignores an all-blank correspondence block (spec-conflict case), confirm with BA, and BR-436 needs another way to change the basic4 count; QA will re-target the TC. | Not a defect (test design) - dev triage 2026-10-05. A standalone BD C record with a wholly blank correspondence block is rejected by validation with C0708 ('correspondence address is required') before any write, matching legacy 8005-VAL-FIRM-PARA. The firm MAILING row is also never deleted by design (legacy Type B = update-or-insert only). QA's expected result (MAILING removed, ALT_ADDRESS gone, basic4 3 -> 2) is not reachable through the feed. QA's reported outcome (no LNAERROR, CNTLRPT 1 BD updated, nothing persisted) cannot come from the described feed on the current code - QA to recheck which day-2 file was actually ingested. | Close as not a defect (test design) once QA confirms the ingested day-2 file. Re-target TC-BR-436: expected = C0708 in LNAERROR, no ADB/ADSI change, CNTLRPT BD updated = 0. If BR-436 genuinely needs a way for a BD to drop ALT_ADDRESS, raise with BA/PO (no feed path exists in legacy either). | ingestion/FeedRecordValidator.java - rule C0708 (BD-mandatory correspondence block), FIRM_ORDER_STANDALONE (8005), addressFailure/isEmptyBlock; ingestion/BundleProcessorImpl.processFirmRecord (validateFirm runs before appointFirm) and contractOperation (CNTLRPT counting); ingestion/ProducerAppointmentServiceImpl.applyFirmAddresses (MAILING never deleted), upsertAddress, updateFirm (UPDATED vs UNCHANGED). | Checked 2026-10-05 against develop @ 003e693 (PR #88 merge; local tree identical). 1) Mapper (FeedRecordMapper.toFirmProfile) reads the correspondence block from cols 307-498 (1-based, inclusive) - same columns QA blanked. 2) FeedRecordValidator rule C0708 makes the block mandatory when entity type = BD; a wholly blank block fails 'correspondence address is required'. C0708 is in the standalone (8005) rule list, and processFirmRecord runs validation before appointFirm, so nothing is written. REPRO: the described day-2 record (BD A995125000, cols 307-498 spaces, standalone) run through the built jar's real mapper + validator -> REJECTED C0708; the day-1 version passes. 3) applyFirmAddresses: Type B (MAILING) is BD-only and never deleted, so even a passing record could not remove ALT_ADDRESS. 4) CNTLRPT: contractOperation counts a standalone update only when updateFirm returns UPDATED, i.e. something actually changed (DEF-011 work); an unchanged re-send is UNCHANGED and not counted. The only UPDATED path that writes no activity row and no contract updt_ts is an address row being INSERTED. So QA's evidence (1 updated, MAILING unchanged, HR2 76/76 unchanged) fits a day-2 record whose correspondence block was identical to day 1, not a blank one. Both the C0708 rule (2026-08-17) and the UPDATED/UNCHANGED gate (2026-09-09) predate the 2026-10-01 run, so build drift does not explain it. | Done 2026-10-05: TC-BR-436 re-targeted and retested PASS. Remaining: BA/PO confirm whether BR-436 needs a feed path to drop a BD's ALT_ADDRESS. Regression retest 2026-10-12: TC-BR-436 PASS 6/6. |  | Not a defect (test design) | Closed - confirmed via re-targeted TC (QA retest PASS 2026-10-05; regression PASS 2026-10-12) | No - re-targeted TC-BR-436 retested PASS 2026-10-05 and 2026-10-12 | BA/PO (BR-436 intent) | Closed as not a defect. Re-targeted TC-BR-436 PASS 2026-10-05. Only the BA/PO BR-436 intent question remains. | No fix needed - code behaves to legacy (C0708 rejection; MAILING never deleted) | [5 empty] | 2026-10-05: Not a defect. A wholly blank correspondence block on a standalone BD record is rejected with C0708 (reproduced against the built code); the BD MAILING row is never deleted by design. The reported run outcome does not match the described feed - please recheck the ingested day-2 file. See Code Analysis. | QA retest 2026-10-05 (TC-BR-436 re-targeted per dev triage, run live, PASS 6/6; day-2 run e039b730-53eb-42c4-9f66-24b0be4663f0, fresh BD A999189000): the standalone C with a wholly blank correspondence block (cols 307-498) is rejected - LNAERROR line C0708 "CORRESPONDENCE ADDRESS" INVALID IN THE "FIRM ENTITY" RECORD - RECORD REJECTED; CNTLRPT NUMBER OF BD CONTRACTS UPDATED IN ADB = 0; address rows, contract updt_ts, activity count and basic4_sections identical before/after (ALT_ADDRESS kept, 3 sections). Dev verdict confirmed - not a defect. TC-BR-436 change (utils/db-verified-cases.brv4.ts): day-2 now asserts C0708 in that day's LNAERROR naming the BD, CNTLRPT BD updated = 0, and no ADB/ADSI change; downloadLnaerrorFile takes an optional feed date. Side note for dev (does not reopen): dev's explanation of the 2026-10-01 count (an address row INSERTED) does not hold - a read-only query on 2026-10-05 shows the original BD A995125000 / A97N4N still has only its two day-1 address rows, contract updt_ts null and only the day-1 AP00AP activity row. The saved day-2 feed was verified blank in cols 307-498 and the ingestion-artifacts ZIP holds outputs only (no input copy), so the 2026-10-01 outcome (no C0708, BD updated = 1) stays unexplained; most likely a different build was deployed then. Same input on the current build behaves correctly. QA regression retest 2026-10-12 (full BRv4 run, playwright.brv4.config.ts, 165/165 passed): TC-BR-436 PASS 6/6 - day-2 standalone C with a wholly blank correspondence block rejected with C0708 in LNAERROR, CNTLRPT BD contracts updated = 0, no ADB/ADSI change (MAILING row and basic4 ALT_ADDRESS retained). Verdict 2026-10-12 09:49:42Z. Closure holds.

## Retest-Recheck + New Bug
Retest / recheck of BRv4 bugs in the latest run, plus the new bug
Latest run: 2026-10-01 06:50Z, playwright.brv4.config.ts, 156 TCs - 155 passed, 1 failed (TC-BR-436). Source: artifacts/results-brv4.json + artifacts/e2e-brv4/verdicts/.
Every retested/rechecked TC below is one of the 156 TCs in that same run - not a separate run. Each verdict's decided time falls inside that run.
Section A - Previously raised bugs (DEF-001 to DEF-016), retested in the latest run
Bug ID | Title | Final Classification | Status in bug log | Related TC(s) retested | In the latest 156-TC run? | Latest run result (checks) | Verdict decided (UTC) | What the latest run verified | Retest / recheck outcome | Remaining action
DEF-RDMS-BRV4-001 | Mandatory BD field not enforced on bundle rejection | Not a defect | Closed - QA retest PASS (B0606) | TC-BR-016 | TC-BR-016: Yes | TC-BR-016: PASS (4/4) | TC-BR-016: 2026-10-01 07:05:52Z | Out-of-set resident state (ZZ) rejects the bundle with B0606, asserted in LNAERROR; a valid control bundle in the same file commits. | Retest PASS - consistent with closure. | None.
DEF-RDMS-BRV4-002 | Type-H (history-only) profile creates a live contract record | Spec conflict | Blocked - BA decision | TC-BR-134 | TC-BR-134: Yes | TC-BR-134: PASS (4/4) | TC-BR-134: 2026-10-01 07:02:17Z | Type-H profile under a different firm for an already-appointed person completes; the outcome is recorded factually - the TC does not assert either behaviour. | Still open - the TC passes only because it records behaviour without judging it. | BA/PO decision on BR-134 wording; then make TC-BR-134 assert the decided outcome.
DEF-RDMS-BRV4-003 | Blank home address on a new record produces no address row | Not a defect | Closed - behaviour confirmed (dev repro) | TC-BR-140 | TC-BR-140: Yes | TC-BR-140: PASS (5/5) | TC-BR-140: 2026-10-01 06:59:47Z | A brand-new record with a blank home address gets no HOME row (dev-confirmed behaviour). | Retest PASS - consistent with closure. | None.
DEF-RDMS-BRV4-004 | Blank DOB leaves birth_date NULL instead of a placeholder | Valid defect | Fixed - QA retest PASS (deployed) | TC-BR-321 | TC-BR-321: Yes | TC-BR-321: PASS (2/2) | TC-BR-321: 2026-10-01 07:00:47Z | Blank DOB on a new person stores the 0001-01-01 placeholder, not NULL. | Fix confirmed - PASS. | None.
DEF-RDMS-BRV4-005 | Second producer under the same firm silently dropped | Not a defect | Closed - QA retest PASS | TC-BR-464 | TC-BR-464: Yes | TC-BR-464: PASS (3/3) | TC-BR-464: 2026-10-01 07:04:10Z | Terminated-with-date subject carries final_org_code + final_date; inactive-without-date subject has final_org_code with NULL final_date. | Retest PASS - consistent with closure. | None.
DEF-RDMS-BRV4-006 | CRD number silently truncated on the master-file write | Working to spec (enhancement) | Fixed - QA retest PASS (deployed) | TC-BR-419 | TC-BR-419: Yes | TC-BR-419: PASS (4/4) | TC-BR-419: 2026-10-01 06:53:13Z | (Bug log lists no TC; the follow-up fix is covered by TC-BR-419.) crd_number is cut to 8 characters on the master; resending the same 10-digit CRD no longer flags a change or writes contract_history. | Fix confirmed - PASS. | Add TC-BR-419 to the bug log's Related TC column.
DEF-RDMS-BRV4-007 | Blank birth date converted to a garbage sentinel timestamp on the master record, not left blank | Not a defect | Closed - QA retest PASS | TC-BR-459 | TC-BR-459: Yes | TC-BR-459: PASS (3/3) | TC-BR-459: 2026-10-01 07:07:29Z | Producer with a DOB carries the real date to the master; producer without one gets the 0001-01-01 placeholder. | Retest PASS - consistent with closure. | None.
DEF-RDMS-BRV4-008 | Producer with a blank relationship start date is silently dropped entirely, with the run reporting zero records skipped | Not a defect | Closed - QA retest PASS | TC-BR-465 | TC-BR-465: Yes | TC-BR-465: PASS (3/3) | TC-BR-465: 2026-10-01 07:07:42Z | Relationship start date carries into all three master date fields; a DB-seeded NULL start date leaves them empty after HR2. | Retest PASS - consistent with closure. | None.
DEF-RDMS-BRV4-009 | A no-change update deletes a producer's blank HOME address row (dev-raised; COBOL-confirmed) | Valid defect | Fixed - awaiting QA 3-day TC-BR-140 retest | TC-BR-140 | TC-BR-140: Yes | TC-BR-140: PASS (5/5) | TC-BR-140: 2026-10-01 06:59:47Z | 3-day scenario: day2 inserts the previously-missing blank HOME row and does not delete it; day3 unchanged resend keeps it. | Retest PASS - this is the 3-day TC-BR-140 retest the bug status is waiting for. | Update status from "Fixed - awaiting QA 3-day TC-BR-140 retest" to "Fixed - QA retest PASS".
DEF-RDMS-BRV4-010 | Producer's home fax number never syncs to the master record | Not a defect | Closed - QA retest PASS | TC-BR-429 | TC-BR-429: Yes | TC-BR-429: PASS (3/3) | TC-BR-429: 2026-10-01 06:53:31Z | Fax fed under WS-HOME-FAX-NUM lands in basic1_business_fax_number on the master (dev-confirmed legacy quirk). | Retest PASS - consistent with closure. | None.
DEF-RDMS-BRV4-011 | A byte-identical resubmission is not treated as a no-op - it still stamps updt_ts and writes new history/activity rows | Valid defect | Fixed - PASS for TC-BR-051/318; TC-BR-319 to re-target | TC-BR-051 TC-BR-319 TC-BR-318 | TC-BR-051: Yes TC-BR-319: Yes TC-BR-318: Yes | TC-BR-051: PASS (3/3) TC-BR-319: PASS (4/4) TC-BR-318: PASS (3/3) | TC-BR-051: 2026-10-01 06:56:10Z TC-BR-319: 2026-10-01 06:56:46Z TC-BR-318: 2026-10-01 07:11:04Z | Byte-identical resubmission is a true no-op (no updt_ts, no activity row) - TC-BR-051/318; re-targeted TC-BR-319: a real change writes contract_history and an identical day3 resend writes none. | Retest PASS for all three, including the re-targeted TC-BR-319. | Update status from "Fixed - PASS for TC-BR-051/318; TC-BR-319 to re-target" to "Fixed - QA retest PASS".
DEF-RDMS-BRV4-012 | Blanking the date of birth on an EXISTING producer wipes a previously-correct value to NULL | Valid defect (duplicate) | Fixed - QA retest PASS (deployed) | TC-BR-322 | TC-BR-322: Yes | TC-BR-322: PASS (3/3) | TC-BR-322: 2026-10-01 06:56:56Z | Blanking the DOB on an existing producer stores the 0001-01-01 placeholder instead of NULL. | Fix confirmed - PASS. | None.
DEF-RDMS-BRV4-013 | HR2's daily sync run has no fault isolation - one node that fails to build crashes the WHOLE day's sync, silently blocking every other legitimate change that cycle | Not a defect (test data) | Closed - retracted by QA | TC-BR-478 TC-BR-482 TC-BR-081 TC-BR-428 | TC-BR-478: Yes TC-BR-482: Yes TC-BR-081: Yes TC-BR-428: Yes | TC-BR-478: PASS (2/2) TC-BR-482: PASS (4/4) TC-BR-081: PASS (5/5) TC-BR-428: PASS (4/4) | TC-BR-478: 2026-10-01 07:03:43Z TC-BR-482: 2026-10-01 07:03:56Z TC-BR-081: 2026-10-01 07:10:40Z TC-BR-428: 2026-10-01 07:16:33Z | All four run in the same suite with correctly sized test ids; HR2 syncs every subject with no crash. | Retest PASS - consistent with the QA retraction. | None.
DEF-RDMS-BRV4-014 | A standalone address update clears line2/phone/fax to blank instead of preserving the prior value, contradicting the documented conditional-field rule | Not a defect | Closed - QA retest PASS | TC-BR-088 | TC-BR-088: Yes | TC-BR-088: PASS (4/4) | TC-BR-088: 2026-10-01 07:00:15Z | line1/city/state/zip always carried; blank line2/phone/fax cleared to blank (dev-confirmed legacy HR1 parity). | Retest PASS - consistent with closure. | BA rewording of BR-088 still pending (see Status Summary).
DEF-RDMS-BRV4-015 | A blank correspondence address on the first BD firm does not reject the bundle (B0608 not enforced) | Not a defect | Closed - confirmed via corrected TC | TC-BR-016 | TC-BR-016: Yes | TC-BR-016: PASS (4/4) | TC-BR-016: 2026-10-01 07:05:52Z | Corrected TC: blank correspondence address on the first BD firm rejects the bundle with B0608, asserted in LNAERROR. | Corrected TC PASS - consistent with closure. | None.
DEF-RDMS-BRV4-016 | contract_history, node_relationship_history and address-on-create writes appear to not fire at all for a genuine change, not just for no-ops - likely an over-broad side effect of the DEF-RDMS-BRV4-011 fix | Not a defect | Closed - confirmed via corrected TC | TC-BR-050 TC-BR-319 TC-BR-140 | TC-BR-050: Yes TC-BR-319: Yes TC-BR-140: Yes | TC-BR-050: PASS (6/6) TC-BR-319: PASS (4/4) TC-BR-140: PASS (5/5) | TC-BR-050: 2026-10-01 06:56:33Z TC-BR-319: 2026-10-01 06:56:46Z TC-BR-140: 2026-10-01 06:59:47Z | Corrected TCs: history tables are written only for the fields they are scoped to (resident state -> contract_history, relationship status -> node_relationship_history); blank HOME row handling as in DEF-009. | Corrected TCs PASS - consistent with closure. | None.
Section B - New bug from the latest run
Bug ID | Title | Final Classification | Status in bug log | Related TC(s) retested | In the latest 156-TC run? | Latest run result (checks) | Verdict decided (UTC) | What the latest run verified | Retest / recheck outcome | Remaining action
DEF-RDMS-BRV4-017 | A standalone BD update that blanks the whole correspondence (mailing) address is reported as a BD contract update but never changes or removes the MAILING address row, so the master record keeps its ALT_ADDRESS section | Not a defect (test design) | Closed - confirmed via re-targeted TC (QA retest PASS 2026-10-05; regression PASS 2026-10-12) | TC-BR-436 (raised from the 2026-10-01 run; re-targeted and retested 2026-10-05) | TC-BR-436: Yes | TC-BR-436: FAIL (3/4) on 2026-10-01 (old expectation) TC-BR-436: PASS (6/6) on 2026-10-05 retest (re-targeted) TC-BR-436: PASS (6/6) on 2026-10-12 regression run | TC-BR-436: 2026-10-01 07:13:27Z (FAIL) TC-BR-436: 2026-10-05 04:24:30Z (PASS) TC-BR-436: 2026-10-12 09:49:42Z (PASS) | Re-targeted TC (2026-10-05): day-2 standalone C with a wholly blank correspondence block is rejected with C0708 in LNAERROR, CNTLRPT BD updated = 0, and address rows / contract updt_ts / activity / basic4_sections are unchanged (ALT_ADDRESS kept). | Re-targeted TC PASS - dev verdict confirmed, consistent with closure as not a defect. Side note for dev (does not reopen): dev's explanation of the 2026-10-01 count (an address row INSERTED) does not hold - a read-only query on 2026-10-05 shows the original BD A995125000 / A97N4N still has only its two day-1 address rows, contract updt_ts null and only the day-1 AP00AP activity row. The saved day-2 feed was verified blank in cols 307-498 and the ingestion-artifacts ZIP holds outputs only (no input copy), so the 2026-10-01 outcome (no C0708, BD updated = 1) stays unexplained; most likely a different build was deployed then. Same input on the current build behaves correctly. Regression 2026-10-12: PASS 6/6 again - closure confirmed. | BA/PO: confirm BR-436 intent. Dev (optional): look at why the 2026-10-01 run gave no C0708 and BD updated = 1.